PRP2 19-Day Project Plan

Fine-Tuning for Guarani Mbya: Low-Resource Writing Assistant

Compressed 3-week realistic roadmap | 19 calendar days

Current situation: Decision Log 1 is already completed: why this project was chosen. The remaining work is to create a complete, assessable fine-tuning workflow: dataset strategy, baseline model test, LoRA fine-tuning, evaluation, simple demo, ethical reflection, Git evidence, and portfolio documentation.

# 1. Main Goal and Success Definition

Main goal: Build a small prototype writing assistant for a low-resource language setting and evaluate whether a fine-tuned model gives useful suggestions or mainly memorizes the training data.

Technical result: Cleaned dataset, baseline outputs, LoRA fine-tuning notebook/script, trained adapter or saved outputs, and a simple Streamlit demo.

Research result: Baseline versus fine-tuned output comparison, plus memorization/generalization checks on held-out examples.

Ethical result: A clear explanation that the project is a prototype and that sensitive Indigenous language data should not be used without consent and community control.

Portfolio result: 5-7 meaningful decision logs, Git commits, screenshots, training logs, evaluation tables, and a final report connected to Learning Outcomes.

# 2. Scope Rules for 19 Days

Do not try to build a perfect language product. Build a small, complete, responsible workflow.

Use Guarani Mbya as the ethical and real-world inspiration, but use only safe public data or simulate low-resource conditions if real data is not clearly safe.

Start with 1,000-3,000 examples. Only expand if the pipeline works early.

Use a small model first. GPT-2 small or another lightweight open model is enough for a prototype.

Use LoRA before considering QLoRA. LoRA is easier to implement, explain, and document.

Keep the Streamlit demo simple. Evaluation is more important than UI polish.

# 3. Compressed 3-Week Roadmap

| Period | Main focus | Output by end of period | Main LOs |
| --- | --- | --- | --- |
| Week 1 Days 1-6 | Scope, dataset, model feasibility, repository setup | Dataset decision, baseline test, repo structure, DL2/DL3 drafts | LO1, LO2, LO6, LO7 |
| Week 2 Days 7-13 | Data cleaning, train/test split, baseline outputs, first LoRA run | Clean dataset, split files, baseline outputs, first training logs, pipeline diagram | LO1, LO3, LO4, LO6 |
| Week 3 Days 14-19 | Evaluation, memorization checks, demo, final portfolio evidence | Evaluation table, demo screenshots, final report, decision logs, evidence map, Git cleanup | LO2, LO4, LO5, LO6, LO7 |

# 4. Day-by-Day Plan

## Week 1 - Decide Before Building (Days 1-6)

Goal: Make the project safe, realistic, and evidence-based before training starts.

| Day | Task | What to do | Evidence to save |
| --- | --- | --- | --- |
| Day 1 | Compress scope and set up repo | Write scope_note.md. Create folders: data/raw, data/processed, notebooks, src, demo, docs, results, portfolio. Add README draft. | scope_note.md, repo commit |
| Day 2 | Search and compare dataset options | Compare 2-3 safe dataset strategies. Include source, license/safety, size, quality, and ethical risk. | dataset_options.md or spreadsheet |
| Day 3 | Choose dataset strategy | Pick the safest and most realistic option. Write source note and limitations. Start DL2. | dataset_source.md, DL2 draft |
| Day 4 | Test base model feasibility | Run a tiny generation test with the chosen base model. Check that the model loads and produces output. | baseline_test.ipynb, screenshots |
| Day 5 | Choose model/fine-tuning approach | Compare small model options and decide LoRA settings at a high level. Start DL3. | model_notes.md, DL3 draft |
| Day 6 | Week 1 checkpoint | Review evidence. Confirm final dataset, base model, evaluation idea, and next week tasks. | weekly_reflection_1.md |

## Week 2 - Build the Training Workflow (Days 7-13)

Goal: Produce a first working fine-tuning workflow, even if the output quality is still weak.

| Day | Task | What to do | Evidence to save |
| --- | --- | --- | --- |
| Day 7 | Clean dataset part 1 | Load data, remove empty rows, broken text, very short examples, and obvious duplicates. | 01_cleaning.ipynb |
| Day 8 | Clean dataset part 2 | Finalize processed dataset. Save before/after counts and examples of removed rows. | processed dataset, cleaning notes |
| Day 9 | Create splits and baseline prompts | Make train/validation/test split. Keep test examples outside training. Create fixed prompts for baseline and evaluation. | train.csv, validation.csv, test.csv, prompts.csv |
| Day 10 | Generate baseline outputs | Run base model on evaluation prompts before fine-tuning. Save outputs in a table. | baseline_outputs.csv |
| Day 11 | Run first LoRA experiment | Train with small settings first. Save config, loss, runtime notes, and sample generations. | training notebook/script, logs |
| Day 12 | Inspect first results | Compare a few baseline and fine-tuned outputs. Note repetition, nonsense output, or early signs of copying. | early_comparison.md |
| Day 13 | Stabilize pipeline and design diagram | Fix broken parts. Create a simple pipeline diagram: data -> cleaning -> split -> base model -> LoRA -> demo -> evaluation. | architecture.png, DL4 draft |

## Week 3 - Evaluate, Demo, and Finish Portfolio (Days 14-19)

Goal: Make the project assessable. The assessor should be able to see what was built, how it was tested, what worked, what failed, and why the limits matter.

| Day | Task | What to do | Evidence to save |
| --- | --- | --- | --- |
| Day 14 | Baseline vs fine-tuned comparison | Use the same held-out prompts for both models. Compare usefulness, repetition, and fluency/pattern quality. | evaluation_table.xlsx or csv |
| Day 15 | Memorization check | Compare generated outputs with training examples using similarity checks and manual inspection. Mark possible copied outputs. | 03_memorization_check.ipynb |
| Day 16 | Build simple Streamlit demo | Input text -> generated suggestion. Add short disclaimer and simple generation settings. | demo/app.py, screenshot |
| Day 17 | Final evaluation examples | Select good output, weak output, and copied/repeated output examples. Explain what each example shows. | evaluation_examples.md |
| Day 18 | Write final documentation | Finish final report, decision logs, ethical reflection, and evidence map. Link evidence to LOs. | final_report, DL5-DL7, evidence_map |
| Day 19 | Final cleanup and submission proof | Clean README, check Git history, remove junk files, add run instructions, export final screenshots. | GitHub repo, final screenshots, final checklist |

# 5. Decision Log Plan

Important: Do not write a decision log for every tiny action. Write logs only for meaningful methodological choices with alternatives, criteria, evidence, and a decision.

| Log | Research question | When | Evidence needed | LO |
| --- | --- | --- | --- | --- |
| DL1 - Project choice | Which PRP2 project fits my GenAI Engineer development best? | Already done | Role reflection, project comparison, project description | LO1 |
| DL2 - Dataset strategy | Which dataset strategy is safe, realistic, and useful for low-resource fine-tuning? | Week 1 | Dataset comparison, source notes, sample rows, ethics notes | LO1 / LO2 |
| DL3 - Model and LoRA approach | Which base model and fine-tuning method fit my hardware, time, and goal? | Week 1 | Model load test, baseline generation, runtime/memory notes | LO1 / LO2 / LO3 |
| DL4 - Preprocessing and split design | How should I clean and split the data to reduce leakage and support evaluation? | Week 2 | Cleaning notebook, duplicate check, train/validation/test files | LO3 / LO4 |
| DL5 - Evaluation method | How can I test whether the model generalizes or memorizes? | Week 3 | Held-out prompts, similarity checks, good/bad/copied examples | LO2 / LO5 |
| DL6 - Demo scope | What demo scope is enough to prove the prototype without overbuilding UI? | Week 3 | Streamlit app, screenshots, user flow, limitations | LO3 / LO4 |
| DL7 - Responsible limits | What would be needed before this could be used responsibly in a real community context? | Week 3 | Ethical reflection, no-native-speaker limitation, consent/control discussion | LO6 / LO7 |

# 6. Evidence Checklist

| Evidence item | Why it matters | Where to store it |
| --- | --- | --- |
| README.md | Explains project, setup, run steps, and limitations. | Repository root |
| scope_note.md | Shows what is inside and outside scope for 19 days. | docs/ |
| dataset_options.md | Shows dataset comparison before the decision. | docs/ |
| dataset_source.md | Explains data source, safety, license/usage, and limitations. | docs/ |
| 01_cleaning.ipynb | Shows preprocessing actions instead of only claiming the data was cleaned. | notebooks/ |
| train/validation/test files | Supports fair evaluation and reduces leakage risk. | data/processed/ |
| baseline_outputs.csv | Shows what the model did before fine-tuning. | results/ |
| training logs/config | Makes fine-tuning traceable and reproducible. | results/training_logs/ |
| fine_tuned_outputs.csv | Shows the result after training. | results/ |
| memorization_check.ipynb | Supports the central question: learning or copying? | notebooks/ |
| evaluation table | Compares baseline and fine-tuned outputs clearly. | results/ |
| demo screenshots | Proves the prototype works visually. | docs/screenshots/ |
| decision logs | Document why important choices were made. | portfolio/decision_logs/ |
| final report | Makes the full workflow understandable to an assessor. | portfolio/ |

# 7. Learning Outcome Mapping

| Learning Outcome | How this project shows it | Concrete evidence |
| --- | --- | --- |
| LO1 - Analysing | Investigating dataset options, model options, fine-tuning method, and project constraints. | DL2, DL3, dataset comparison, baseline tests |
| LO2 - Advising | Making justified recommendations about dataset safety, model choice, and responsible limits. | Decision logs, final recommendations, ethics section |
| LO3 - Designing | Designing the fine-tuning pipeline, data split, evaluation method, and demo flow. | Architecture diagram, preprocessing plan, demo design |
| LO4 - Realising | Building and testing the working fine-tuning workflow and demo. | Code, notebooks, training logs, Streamlit app, Git commits |
| LO5 - Managing & Controlling | Monitoring model behavior, checking memorization, identifying weak outputs, and improving settings. | Evaluation table, memorization check, iteration notes |
| LO6 - Professional Standard | Using a structured method, evidence-based decisions, ethical reflection, and Git documentation. | Project plan, decision logs, evidence map, source notes |
| LO7 - Personal Leadership | Managing the 19-day plan, asking for feedback, reflecting on limits, and adjusting scope realistically. | Weekly reflections, feedback notes, final reflection |

# 8. Risk and Fallback Plan

| Risk | What can go wrong | Fallback action |
| --- | --- | --- |
| Dataset is unsafe or unclear | Real language data may be sensitive or not clearly allowed. | Use safe public data or simulate low-resource conditions. Document the decision honestly. |
| Training is too heavy | Model may fail because of memory or time limits. | Use fewer examples, fewer epochs, smaller model, smaller batch size, or LoRA only. |
| Output quality is weak | Model may produce repetitive or low-quality suggestions. | Still evaluate honestly. Weak results are acceptable if analysis is strong. |
| High memorization | Model may copy training examples instead of learning patterns. | Show this as a finding and explain why it limits real-world use. |
| No native speaker review | Language quality cannot be properly verified. | Avoid strong claims about correctness. Focus on workflow and limitations. |
| Time pressure | Too much UI or documentation polish may weaken core evidence. | Cut UI polish first. Protect dataset, baseline, training, evaluation, and decision logs. |

# 9. Git and Work Rhythm

Commit after each meaningful step, not only at the end.

Use simple prefixes: docs, feat, test, experiment, fix, refactor.

Link important commits in decision logs as evidence.

Keep large generated files out of Git if needed, but document where they are stored.

Every week should end with a short reflection and visible evidence, not only unfinished code.

| Example commit | Meaning |
| --- | --- |
| docs: add 19-day PRP2 project plan | Shows project planning and scope control. |
| docs: compare dataset options | Supports DL2 dataset strategy. |
| test: run baseline generation on held-out prompts | Supports model feasibility and evaluation. |
| feat: implement LoRA fine-tuning pipeline | Shows realization of training workflow. |
| test: add memorization similarity check | Supports LO5 monitoring and evaluation. |
| feat: create Streamlit writing assistant demo | Shows the working prototype. |
| docs: add final evaluation and responsible limits | Supports portfolio completion. |

# 10. What to Cut If Time Becomes Tight

Protect the core evidence first: dataset -> baseline -> fine-tuning -> evaluation -> decision logs. Cut these items first if needed:

Do not polish the demo UI. Keep it simple.

Do not test many models. One baseline and one fine-tuned version is enough.

Do not chase perfect output quality. Honest evaluation is more valuable.

Do not write too many decision logs. Five to seven meaningful logs are enough.

Do not expand the dataset if the first smaller dataset already supports the workflow.

# 11. Definition of Done

A clear scope note explaining what the project does and does not do.

A safe dataset strategy with source explanation and limitations.

A cleaned dataset and train/validation/test split.

Baseline model outputs before fine-tuning.

A LoRA fine-tuning notebook or script with saved settings and logs.

Generated outputs from the fine-tuned model.

A simple Streamlit demo that gives writing suggestions.

An evaluation section comparing useful, weak, and memorized outputs.

A responsible ethical reflection explaining consent, community control, and prototype limits.

5-7 meaningful decision logs including the already completed project choice log.

A Git history that shows development steps and experiments.

A final report or portfolio page connecting evidence to Learning Outcomes.

# 12. Simple Daily Working Rule

Every project day should create one small visible artifact: a note, dataset file, notebook result, screenshot, commit, evaluation table, or decision log update. If nothing can be shown, the work is hard to assess.

When asking for guidance, ask about the current artifact, not the whole project. Example: "I found these two datasets; which one is safer and easier to justify?" or "This is my baseline output; is it enough evidence for DL3?"

# 13. Source Documents Used for This Plan

Guarani Mbya Writing Assistant - Clear Short Project Description

Fine-Tuning for Guarani Mbya: AI for Endangered Languages project description

Portfolio Documentation Guide

GenAI Project Learning Outcomes Guide

Decision Log Coaching & Documentation Guide

How I Will Use Git in This Project

Decision Log - Project Choice

Previous 4-week PRP2 Fine-Tuning Project Plan